## Reference Documents
Reference Documents Status
External Documents | Document Number | Resp. Org | Resp. Assignee | Date | Date: Status Impact (if any)
Near Earth Network User's Guide | 453-NENUG | NEN | Kevin McCartny | 2015-07-15 | Rev 1
Space Netowrk User's Guide | 450-SNUG | SN | Frank Stocklin | August, 2007 | Rev 9
NASA Systems Engineering Handbook | NASA/SP-2007-6105 | HQ | NASA Systems Engineers | December, 2007 | Original
Command Telemetry format Interface Control Document (ICD), IRIS Observatory | A101-RQ-09-0364 | IRIS Project | NASA Systems Engineers |  | Rev C
Security of Information Technology | NPR 2810.1A | NASA | NASA Systems Engineers
NASA Integrated Services Network (NISN) Internet Protocol Operational Network (IONet) Security Policy | 700-DOC-029 | NISN | NASA Systems Engineers
Recommended Security Controls for Federal Information Systems | NIST SP 800-53
Systems Engineering Procedural Requirements | 7123 | NASA | NASA Systems Engineers | 2006-03-13
7150.2B
Build Description for NASA/Goddard Demonstration | VHR_3200_Goddard_Build_Description | ViSat | ViSat | Original
VHR-3200 10GbE Interface Description | 10GbE_Interface_Description | ViSat | ViSat | Original
Interface Control Document, VHR-1200/3200, Data-Client Interface | DCI_ICD_Rev004 | ViSat | D. Parks | 2015-01-01
VDP DRI ICD | DRI_ICD_Rev006 | ViSat | D. Parks | 2014-07-18
Operation and Maintenance Manual | VHR-3200_Manual | ViSat | ViSat | december, 2015 | Proprietary notice
Data Processor Operation and Maintenance Manual | VDP_Manual | ViSat | Original Instructions | October, 2015 | Proprietary notice
General Guidance:
Preface your status update with either MM/YY: (preferred) or MM/DD/YY: and insert this month’s status ABOVE status from previous months.
Use red text only to highlight special items of interest (i.e., no need to highlight this month’s changes)
DO NOT delete entries. Instead, hide rows that you don't plan to display.
Specific Guidance:
Include ALL external documents on which the team is dependent.
If a document is not needed, it should not appear on this slide (i.e., each document must show a need date).
In the status field, indicate the state of the document and describe impacts if the document is not on time:
MM/YY: Draft = not yet released for external review
MM/YY: Preliminary = available for external review
MM/YY: Complete = Configured by FSW Team, controlled changes only
MM/YY: Submitted = Submitted to Project for Baselining
MM/YY: Project Baseline = Configured by Project, controlled changes only.
MM/YY: Rev. = 1, if initial Baseline

## current Document status
Title Phase 1 (*SRR nov 2014) | Ref Phase 1 SRR 2014 | gitlab phase 1 file | Title from June 15 Phase II SRR | relevant phase | june 15 srr Document ref | Gitlab file name | Proposed Reference june2016 | Document | Proposed Phase II title | Proposed Reference july 16 DAPHNE / NGIN | % Complete | Resp. CCB | Orig. org | Assignee | Planned Date | Baseline Date | Date: Status Impact (if any) | Content additions Per SEHB Entry Criteria
*Test Plan for the NENG Phase 1 | SCNS-NEN-Plan-0001 | SCNS-NEN-PLAN-0001.doc | Test Plan for the NENG Phase II | 2 | NEN-Plan-0001 | NEN-PLAN-0002.docx | NEN-Plan-0002 | Integration, Verification and Test Plan | Integration and Test Plan for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TPlan-Rev1 / TBD | 75% | DAPHNE | 566 | Perrine |  |  |  | q. verification and validation approach;
Acceptance Test Procedure Phase 1 for the Near Earth Network (NEN) Gateway (NENG) | SCNS-NEN-PLAN-0001 | SCNS-NEN-PLAN-0001_Rev003.doc,NENG_Test_Procedure_dropv4.docx | Test Procedure |  | NEN-TP-0001 | NEN-TP-0002.docx | NEN-TP-0002 | Integration, Verification and Test Procedure | Acceptance Test Procedure for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TP-Rev1 / na | 75% | DAPHNE | 566 | Perrine |  |  | Draft, includes integration procedures
Acceptance Test Report Phase 1 for the Near Earth Network (NEN) Gateway (NENG) , Acceptance Test Report for the Near Earth Network Gateway (NENG) Delivery to Alaska Satellite Facility | NEN-Report-0001 | SCNS-NEN-Report-0001_Rev04, NENG_Test_Report_drop7.docx | Test Report |  | NEN-Report-0001 | SCNS-NEN-REPORT-0001Rev04.docx | NEN-Report-0002 | Acceptance Test Report | Acceptance Test Report for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TReport-Rev1 / TBD | 0% | DAPHNE | 566 | Perrine
none |  |  | Software Management Plan | 1&2 | NEN-SMP-0001 | NENG-SMP-0001softwaremanagementplan.doc | NEN-SMP-0001 | Software Management Plan, includes: SEMP, Risk Management, Safety Assurance, &Software Assurance. | Data Acquisition Processing and Handling Network Environment (DAPHNE) Software Management Plan (SMP) | NENG-SMP-0001 (566-DAPHNE-SMP-Rev2) | 100% | DAPHNE | 566 | Perrine |  |  | Contains needed SEMP elements | Software Management Plan, includes: SEMP, Risk Management, Safety Assurance, &Software Assurance, i. technology development maturity assessment plan; and software development plan
none |  |  | Configuration Management Plan | 1&2 | NEN-CM-0001 | NENG-CMP-0001.doc | NENG-CMP-0001 | Configuration Management Plan | Data Acquisition Processing and Handling Network Environment (DAPHNE) Configuration Management Plan | 566-DAPHNE-CMP-Rev2 / na | 100% | DAPHNE | 566 | Salem El Nimri |  |  | Original | same
Concept of Operations | NEN-COP-0001 | NENG-CONOPS-0001.doc | Concept of Operations | 1&2 | NEN-COP-0001 | ConOps_V2.docx | NEN-CONOPS-0001 | Concept of Operations | Near Earth Network Data Acquisition Processing and Handling Network Environment Concept of Operations | 566-DAPHNE-CONOP-Rev2 / na | 100% | DAPHNE | 566 | Perrine |  |  | Original: file name NEN-CONOPS-0001.docx | same
*Design Specification for the NENG Task | SCNS-NEN-SPEC-0001 | SCNS-NEN-SPEC-0002_Rev3tradestudies.docx | not listed | 1&2 | not listed | SCNS-NEN-SPEC-0002_Rev3tradestudies.docx | SCNS-NEN-SPEC-0002 (consider NENG-spec-02) | Design and Architecture | Design Specification for the Near Earth Network Gateway (NENG) Task | 566-NENG-spec-Rev1 / SCNS-NEN-SPEC-0002 | 100% | DAPHNE | 566 | Salem El Nimri |  |  |  | . system software functionality description;
|  | NENG_Software_Classification_Rationale v2.docx | same |  | NENG_Software_Classification_Rationale | NENG_Software_Classification_Rationale v3.docx | none | Classification Rationale | Data Acquisition Processing and Handling Network Environment (DAPHNE) software Classification Rationale | 566-DAPHNE-RATI-Rev4 | 95% | DAPHNE | 566 | Perrine
[6 empty] | RequirementsVerificationTraceabilityMatrix.xlsx | none | Requirements Verification Traceability Matrix (RVTM) | Requirements Verification Traceability Matrix (RVTM)- Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-RTVM-Rev2 / na | 100% | DAPHNE | 566 | Perrine
| SCNS-NEN-OPI-0001 | 2012_05_02_CTL_Users_Guide.docx | NEN ICD Between NENG and M&C/LINUX NENG Users Guide | 1&2 | 453-ICD-MC-001/NEN-UsersGuide-0001 | 2012_05_02_CTL_Users_Guide.docx | 453-ICD-MC-001 | DAPHNE to M&C ICD/user guide | DAPHNE and M&C ICD CTL Users Guide | 566-DAPHNE-M&C_ICD-Rev1 | 100% | DAPHNE | 566 | Kaul
Users Guide Phase 1 for the Near Earth Network (NEN) Gateway (NENG) | SCNS-NEN-OPI-0001 | SCNS-NEN-UserGuide-0001_Rev11.docx | none |  | ,none | ,TBD | SCNS-NEN-OPI-0003 | DAPHNE Operations User Guide | Users Guide Data Acquisition and Processing Environment (DAPHNE) | 566-DAPHNE-UG-Rev1 / TBD | 0% | DAPHNE | 566 | Perrine
[8 empty] | DAPHNE Maintenance Plan | DAPHNE Maintenance Plan | 566-DAPHNE-MaintPLAN-Rev1 | 90% | DAPHNE | 566 | Perine
*Commissioning Plan/Procedures | SCNS-NEN-PLAN-xxxx | notional |  |  |  | NEN-PLAN-0002.docx | NEN-Plan-0002 | Commissioning Plan | Data Acquisition Processing and Handling Network Environment (DAPHNE) Commissioning Plan | 566-DAPHNE-CPlan-Rev1 / TBD | 95% | NGIN | 566 | Perrine
*NEN ICD Between NENG and IRIS MOC | 453-ICD-IRIS/NENGG | 453-ICD-IRIS_NENG.docx | NEN ICD Between NENG and IRIS MOC | 1&2 | 453-ICD-IRIS/NENG | 453-ICD-IRIS_NENG.docx | 453-ICD-IRIS/NENG | NEN/NENG/IRIS ICD | NEN ICD Between NENG and IRIS MOC | 453-ICD-IRIS/NENG | 100% | NGIN | IRIS | Salem El Nimri |  |  | Signed; file name: 453-ICD-IRIS_NENG.docx
*Requirement Specification Phase 1 for the NENG | SCNS-NEN-REQT-0001 | SCNS-NEN-REQT-0002 | Requirements Specificaiton Phase II | 2 | NEN-REQT-0001 | SCNS-NEN-DAPHNE-REQT-010 TTreview rev19may16.doc | NEN-REQT-010 | Requirements (SRD) | Requirements Specification for the Data Acquisition Processing and Handling Environment (DAPHNE) | 566-DAPHNE-REQT-Rev2 / SCNS-NEN-REQT-0008 | 100% | NGIN | 566 | Perrine |  |  |  | same
[8 empty] | NEN/DAPHNE/NISAR ICD | NEN ICD Between DAPHNE and NISAR MOC | 453-ICD-NISAR/DAPHNE | 0% | NGIN | NISAR | Salem El Nimri
[8 empty] | Amerigent SLE Interface Standard Manual | Amerigent SLE interface standard manual | NA | 100% | Vendor | Vendor
(Cortex Manual) |  |  | none | 2 | none | viasat_vhr_icd.pdf | viasat_vhr_icd | Viasat Rx manual and ICD | Viasat VHR 3200 ICD | NA | 100% | Viasat | Viasat | viasat
[7 empty] | ? | ? | Maintenance Manual | 566-DAPHNE-MAINM | 0% | DAPHNE | 566 | Perrine

## simpleformaug16
DAPHNE Related Document | Resp. CCB | Here is NEN's 19 August input | DAPHNE Related Document | Resp. CCB
Commissioning Plan | NEN NGIN |  | Commissioning Plan | NEN (NGIN)
NEN/NENG/IRIS ICD | NEN NGIN |  | NEN/NENG/IRIS ICD | NEN (NGIN)
NEN/DAPHNE/NISAR ICD | NEN NGIN |  | NEN/DAPHNE/NISAR ICD | NEN (NGIN)
Requirements (SRD) | NEN NGIN |  | Requirements (SRD) | NEN (NGIN)
DAPHNE to M&C ICD/user guide | DAPHNE |  | DAPHNE to M&C ICD/user guide | Code 566/DAPHNE
DAPHNE operations user guide | DAPHNE |  | DAPHNE operations user guide | Code 566/DAPHNE
Integration and Test Plan | DAPHNE |  | Integration and Test Plan | Code 566/DAPHNE
Integration and Test Procedure | DAPHNE |  | Integration and Test Procedure | Code 566/DAPHNE
Acceptance Test Report | DAPHNE |  | Acceptance Test Report | Code 566/DAPHNE
Software Management Plan | DAPHNE |  | Software Management Plan | Code 566/DAPHNE
Configuration Management Plan | DAPHNE |  | Configuration Management Plan | Code 566/DAPHNE
Conops | DAPHNE |  | Conops | Code 566/DAPHNE
Design and Architecture | DAPHNE |  | Design and Architecture | Code 566/DAPHNE
RVTM | DAPHNE |  | RVTM | Code 566/DAPHNE
Amerigent SLE interface standard manual | Amerigent (or other SLE vendor) |  | Amerigent SLE interface standard manual | Amerigent (or other SLE vendor)
Viasat Rx manual | Viasat |  | Viasat Rx manual | Viasat

## currenttreedonotedit
Do not edit here | Document | Proposed Phase II title | Proposed Reference july 16 DAPHNE / NGIN | % Complete | Resp. CCB | Assignee | Document | Resp. CCB | % Complete
| Integration, Verification and Test Plan | Integration and Test Plan for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TPlan-Rev1 / TBD | 0.75 | DAPHNE | Perrine | Integration, Verification and Test Plan | DAPHNE | 75%
| Integration, Verification and Test Procedure | Acceptance Test Procedure for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TP-Rev1 / na | 0.75 | DAPHNE | Perrine | Integration, Verification and Test Procedure | DAPHNE | 75%
| Acceptance Test Report | Acceptance Test Report for the Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-TReport-Rev1 / TBD | 0 | DAPHNE | Perrine | Acceptance Test Report | DAPHNE | 0%
| Software Management Plan, includes: SEMP, Risk Management, Safety Assurance, &Software Assurance. | Data Acquisition Processing and Handling Network Environment (DAPHNE) Software Management Plan (SMP) | NENG-SMP-0001 (566-DAPHNE-SMP-Rev2) | 1 | DAPHNE | Perrine | Software Management Plan, includes: SEMP, Risk Management, Safety Assurance, &Software Assurance. | DAPHNE | 100%
| Configuration Management Plan | Data Acquisition Processing and Handling Network Environment (DAPHNE) Configuration Management Plan | 566-DAPHNE-CMP-Rev2 / na | 1 | DAPHNE | Salem El Nimri | Configuration Management Plan | DAPHNE | 100%
| Concept of Operations | Near Earth Network Data Acquisition Processing and Handling Network Environment Concept of Operations | 566-DAPHNE-CONOP-Rev2 / na | 1 | DAPHNE | Perrine | Concept of Operations | DAPHNE | 100%
| Design and Architecture | Design Specification for the Near Earth Network Gateway (NENG) Task | 566-NENG-spec-Rev1 / SCNS-NEN-SPEC-0002 | 1 | DAPHNE | Salem El Nimri | Design and Architecture | DAPHNE | 100%
| Classification Rationale | Data Acquisition Processing and Handling Network Environment (DAPHNE) software Classification Rationale | 566-DAPHNE-RATI-Rev4 | 0.95 | DAPHNE | Perrine | Classification Rationale | DAPHNE | 95%
| Requirements Verification Traceability Matrix (RVTM) | Requirements Verification Traceability Matrix (RVTM)- Data Acquisition Processing and Handling Network Environment (DAPHNE) | 566-DAPHNE-RTVM-Rev2 / na | 1 | DAPHNE | Perrine | Requirements Verification Traceability Matrix (RVTM) | DAPHNE | 100%
| DAPHNE to M&C ICD/user guide | DAPHNE and M&C ICD CTL Users Guide | 566-DAPHNE-M&C_ICD-Rev1 | 1 | DAPHNE | Kaul | DAPHNE to M&C ICD/user guide | DAPHNE | 100%
| DAPHNE Operations User Guide | Users Guide Data Acquisition and Processing Environment (DAPHNE) | 566-DAPHNE-UG-Rev1 / TBD | 0 | DAPHNE | Perrine | DAPHNE Operations User Guide | DAPHNE | 0%
| DAPHNE Maintenance Plan | DAPHNE Maintenance Plan | 566-DAPHNE-MaintPLAN-Rev1 | 0.9 | DAPHNE | Perine | DAPHNE Maintenance Plan | DAPHNE | 90%
| Commissioning Plan | Data Acquisition Processing and Handling Network Environment (DAPHNE) Commissioning Plan | 566-DAPHNE-CPlan-Rev1 / TBD | 0.95 | NGIN | Perrine | Commissioning Plan | NGIN | 95%
| NEN/NENG/IRIS ICD | NEN ICD Between NENG and IRIS MOC | 453-ICD-IRIS/NENG | 1 | NGIN | Salem El Nimri | NEN/NENG/IRIS ICD | NGIN | 100%
| Requirements (SRD) | Requirements Specification for the Data Acquisition Processing and Handling Environment (DAPHNE) | 566-DAPHNE-REQT-Rev2 / SCNS-NEN-REQT-0008 | 1 | NGIN | Perrine | Requirements (SRD) | NGIN | 100%
| NEN/DAPHNE/NISAR ICD | NEN ICD Between DAPHNE and NISAR MOC | 453-ICD-NISAR/DAPHNE | 0 | NGIN | Salem El Nimri | NEN/DAPHNE/NISAR ICD | NGIN | 0%
| Amerigent SLE Interface Standard Manual | Amerigent SLE interface standard manual | NA | 1 | Vendor | 0 | Amerigent SLE Interface Standard Manual | Vendor | 100%
| Viasat Rx manual and ICD | Viasat VHR 3200 ICD | NA | 1 | Viasat | viasat | Viasat Rx manual and ICD | Viasat | 100%

## orig29feb16ver
Documents Status
Document Title | Document Offical Title | Resp. Org. | Assignee | Resp. CCB | Planned Date | % Complete | Baseline Date | Date: Status Impact (if any)
Team Process Documents
Software Management Plan | NEN-SMP-0001 | 566 |  | DAPHNE |  | 95% |  | Original
Configuration Management Plan | NEN-CM-0001 | 566 | Salem El Nimri | DAPHNE | 2015-10-30 | 95% |  | Original
Test Plan Procedures | NEN-Plan-0001 | 566 | Anne Koslosky | DAPHNE |  | 90% |  | Draft
Test Plan Procedures Report | NEN-Report-0001 | 566 | Anne Koslosky | DAPHNE |  | 0% |  | Need DAPHNE for tests
System Implementation Plan (SIP) | 566-NENG-PLAN-001 | 566 | Salem El Nimri | DAPHNE | 2015-10-30 | 100% |  | Original
Design Guidelines | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
Team Deliverable Technical Documents
Requirements Specificaiton (SRD) | NEN-REQT-0001 | 566 | Salem El Nimri | DAPHNE | 2015-10-30 | 100% |  | Original
User's Guide(CMD&TLM Defined) | NEN-UsersGuide-0001 | 566 | Deepak | DAPHNE |  | 75% |  | Original
Integration & Acceptence Test Plan | NEN-TP-0001 | 566 | Anne Koslosky | DAPHNE |  | 0% |  | Original
Integration & Acceptence Test Procedures Report | NEN-Report-0001 | 566 | Anne Koslosky | DAPHNE |  | 0% |  | Need DAPHNE for tests
Concept of Operations | NEN-COP-0001 | 566 | Martin Perrine | DAPHNE | 2015-10-30 | 95% |  | Original
Interface Control Document with IRIS | 453-ICD-IRIS/NENGG | 566 |  | DAPHNE |  | 100% |  | Signed
Interface Control Document with M&C | 453-ICD-MC-001 | 566 |  | DAPHNE |  | 95%
Interface Control Document with IF Receiver |  |  |  | DAPHNE
RequirementsVerificationTraceabilityMatrix (RTVM) | RequirementsVerificationTraceabilityMatrix | 566 | Martin Perrine | DAPHNE |  | 95% |  | Draft
Transition Plan Document | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
ATRR package | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
Acceptance Test Results | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
Acceptance Data Package | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
Build Test Plan | Anne's Recommendations | TBD | [5 empty] | Team rejected this document
Build Test Procedures | Anne's Recommendations | TBD | [5 empty] | Team rejected this document

## orig Document Status Phase II
Phase II Documents Status
Document Title orig phase 1 | proposed doc phase II | Document Offical Title | file name | Resp. Org. | Assignee | Resp. CCB | Planned Date | % Complete | Baseline Date | Date: Status Impact (if any) | Orig from Phase I | Non Gitlab CM
Team Process Documents
Software Management Plan | Software Management Plan | NEN-SMP-0001 | NENG-SMP-0001softwaremanagementplan.doc | 566 |  | DAPHNE |  | 95% |  | Original | y
Configuration Management Plan | Near Earth Network (NEN) Gateway (NENG) Configuration Management Plan (CMP) | NEN-CMP-0001 | NENG-CMP-0001.doc | 566 | Salem El Nimri | DAPHNE | 2015-10-30 | 95% |  | Original | y
System Implementation Plan (SIP) | NENG System Implementation Plan (SIP) | 566-NENG-PLAN-00x | NENG-System-Implementation-Plan_10-13-15.doc | 566 | Salem El Nimri | DAPHNE | 2015-10-30 | 100% |  | Original | updates
Team Deliverable Technical Documents
Concept of Operations | Concept of Operations |  | ConOps_V2.docx | 566 | Martin Perrine | DAPHNE |  | 100% |  | DAPHNE update complete | y
Requirements Specification Phase II for the Near Earth Network (NEN) Gateway (NENG) | Requirements Specification for Data Acquisition Processing and Handling Environment (DAPHNE) |  | SCNS-NEN-REQT-0008.doc | 566 | Martin Perrine | DAPHNE |  | 100% |  | SRR complete, Performing delta SRR in June 2016 version 10. Note this was called NEN-REQT-0001 at SRR. | updates | NEN--NGIN
User's Guide(CMD&TLM Defined) | DAPHNE User's Guide (CMD&TLM Defined) | CTL Users Guide | 2012_05_02_CTL_Users_Guide.docx | 566 | Deepak | DAPHNE |  | 95% |  | Need to update post development | y | NEN--NGIN
Test Plan Procedures | Test Plan for the Near Earth Network (NEN) Gateway (NENG) Phase 2 | NEN-PLAN-0001(needs update) | NEN-PLAN-0001 AKoslosky (2).doc | 566 |  | DAPHNE |  | 75% |  | Draft | updates
| DAPHNE Test and Integration Procedure |  | NENG-TP-001 |  |  |  |  | 30%
Test Report | DAPHNE Test Report |  |  | 566 |  | DAPHNE |  | 0% |  | Need DAPHNE for tests | updates
Integration & Acceptence Test Plan | Integration & Acceptence Test Plan- Phase II | included in test plan | NEN-PLAN-0001 AKoslosky (2) | 566 |  | DAPHNE |  | 0% |  | Integration is included in Test plan | y | NEN--NGIN
Integration & Acceptence Test Procedures Report | Integration & Acceptence Test Report Phase II | include in test report |  | 566 |  | DAPHNE |  | 0% |  |  | y | NEN--NGIN
Near Earth Network (NEN) Interface Control Document (ICD) Between the NEN Gateway (NENG) and the Interface Region Imaging Spectrograph (IRIS) Mission Operations Center (MOC) | DAPHNE Interface Control Document with NISAR Mission |  |  | 566 |  | DAPHNE |  | 0% |  | Signed | n | NEN--NGIN
Interface Control Document with M&C | Interface Control Document with M&C-- |  |  | 566 |  | DAPHNE |  | 0% |  |  | y | NEN--NGIN
Interface Control Document with IF Receiver | Interface Control Document with IF Receiver--TBD (Rx user manual) |  |  |  |  | DAPHNE |  | 0% |  | May be just the Receiver manual. | n | NEN--NGIN
| RequirementsVerificationTraceabilityMatrix (RTVM)--Phase II | RequirementsVerificationTraceabilityMatrix | RequirementsVerificationTraceabilityMatrix.xlsx | 566 | Martin Perrine | DAPHNE |  | 100% |  | Draft | updates
| DAPHNE Standard Mission Services and Interface. |  |  | 566 | Martin Perrine |  |  | 0% |  | Idea to support NEN standard service model |  | NEN--NGIN
Users Guide Phase 1for the Near Earth Network (NEN) Gateway (NENG) | Setup Guide and Maintence Manual for DAPHNE | [6 empty] | 30
Status: (in addition to explanation)
Draft = not yet released for external review
Preliminary = available for external review
Complete = Configured by FSW Team, controlled changes only
Original = Submitted to Project for Baselining
Signed = Configured by Project, controlled changes only, and signed.
Rev. = 1, if initial Baseline
On tables containing “Date: Status” columns, preface your status update with either MM/YY: (preferred) or MM/DD/YY: and insert this month’s status above status from previous months.
For those slides showing open / closed items, always present the closure status in the BSR one time before hiding the item in future BSRs (i.e., never go from Open to invisible from one BSR to the next!)
Remember to think about and include process-related items as applicable to each topic

## anneMariessuggestions
Transition Plan Document | Anne's Recommendations | TBD | Team rejected this document
ATRR package | Anne's Recommendations | TBD | Team rejected this document
Acceptance Test Results | Anne's Recommendations | TBD | Team rejected this document
Acceptance Data Package | Anne's Recommendations | TBD | Team rejected this document
Build Test Plan | Anne's Recommendations | TBD | Team rejected this document
Build Test Procedures | Anne's Recommendations | TBD | Team rejected this document
Design Guidelines | Anne's Recommendations | TBD | Team rejected this document

## ccb
DAPHNE Related Document | Resp. CCB | Per Bruce Thoman email 8/19/16
Commissioning Plan | NEN (NGIN)
NEN/NENG/IRIS ICD | NEN (NGIN)
NEN/DAPHNE/NISAR ICD | NEN (NGIN)
Requirements (SRD) | NEN (NGIN)
DAPHNE to M&C ICD/user guide | Code 566/DAPHNE
DAPHNE operations user guide | Code 566/DAPHNE
Integration and Test Plan | Code 566/DAPHNE
Integration and Test Procedure | Code 566/DAPHNE
Acceptance Test Report | Code 566/DAPHNE
Software Management Plan | Code 566/DAPHNE
Configuration Management Plan | Code 566/DAPHNE
Conops | Code 566/DAPHNE
Design and Architecture | Code 566/DAPHNE
RVTM | Code 566/DAPHNE
Amerigent SLE interface standard manual | Amerigent (or other SLE vendor)
Viasat Rx manual | Viasat

## sehb srr docs
DAPHNE location | SEHB SRR entry:
SRD | a. system requirements document;
Design? | b. system software functionality description;
conops | c. updated ConOps;
NEN SRD | d. updated mission requirements, if applicable;
SMP | e. baselined SEMP;
SMP to add | f. risk management plan;
Design? | g. preliminary system requirements allocation to the next lower level system;
h. updated cost estimate;
SMP to add | i. technology development maturity assessment plan;
SMP to add | j. updated risk assessment and mitigations (including PRA, as applicable);
to add | k. logistics documentation (e.g., preliminary maintenance plan);
NA | l. preliminary human rating plan, if applicable;
SMP | m. software development plan;
SMP | n. system SMA plan;
CMP | o. CM plan;
doc tree | p. initial document tree;
Test plan | q. verification and validation approach;
SMP | r. preliminary system safety analysis; and
NA | s. other specialty disciplines, as required.